## Scrum_3_16_2021
Team Members | What was completed in the last 24 hours? | What will be completed in the next 24 hours? | Any impediments?
Jonathan Gamble | Used SpecFlow and Selenium to develop the BDD Test for the create profile user story | Integrate Test Project into the Dev to Test Release Pipeline | I have no impediments at this time.
Terrence Shannon | Testing of deployed features within test and production environments. Catalogued daily scrum notes for documentation and task coordination | Learn more about BDD testing and how to generate tests using BDD automation | I have no impediments at this time.
Shakera Dean | Worked on creating the burndown chart to display the teams progress and created the excel sheet to document task completions | Continue working on the burndown chart to make any changes needed to make sure the chart reflects the correct information | I have no impediments at this time.
Miche Isaac | Started testing App UI in multiple platform | Continue testing UI and record deficiency | To be listed as testing progress
Wyatt Landers | Worked on developing hand drawn prototypes for future front end pages, as well as continued learning how to better utilize BlazorStrap to fit the ideal front-end experience. | Continue pursuing further knowledge on BlazorStrap to better understand how to apply my BootStrap knowledge in accordance with it. | No impediments at this time.

## Scrum_3_24_2021
Team Members | What was completed in the last 24 hours? | What will be completed in the next 24 hours? | Any impediments?
Jonathan Gamble | Developed Sprint 1 Documentation for deliverable. | Begin working on the development for Search For Games user story for Sprint 2. | I have no impediments at this time.
Terrence Shannon | Testing of deployed features within test and production environments. Catalogued daily scrum notes for documentation and task coordination | Continue development of BDD tests for test automation; Ensure all user stories for Sprint 2 meet definition of ready prior to beginning of Sprint 2 | No impediments at this time.
Shakera Dean | Tested the website for sprint 1 and edited the burndown chart so it reflects the tasks better | Work with the team to finish all tasks that is needed for sprint 1 | No impediments at this time.
Miche Isaac | Started testing App UI in multiple platform | Continue testing UI and record deficiency | To be listed as testing progress
Wyatt Landers | Continued learning how to better utilize BlazorStrap to fit the ideal front-end experience. Implemented front end changes for Registration and Home page. | Continue pursuing further knowledge on BlazorStrap to better understand how to apply my BootStrap knowledge in accordance with it. Apply learned knowledge to front end development. | No impediments at this time.