## Sprint 2 Scrum 1
Team Members | What was completed in the last 24 hours? | What will be completed in the next 24 hours? | Any impediments?
Jonathan Gamble | Integrated code from the tasks related to the first three user stories for sprint 2 into the development branch which pushed the changes to the test environment. This was done to allow team members to begin testing the new changes | Begin working on View User Profile user story | No impediments at this time
Terrence Shannon | Reviewed video tutorials for Specflow and Selenium to continue to assist with BDD test case development tasks. Testing of Sprint 2 tasks within test environment | Develop additional BDD test case | No impediments at this time
Shakera Dean | Created a burndown chart for sprint 2 and added a new tab in the scrum excel document so the team can log their progress. Checked the backlog and task for sprint 2 to see the progress that has been made. | Continue to watch the kanban board for changes in the tasks so I can edit the burndown chart accordingly. | No impediments at this time
Miche Isaac | Review criteria for sprint 2 Continued testing PlayTogether web interface | Review Part 3 - Sprint 2 criteria | No impediments at this time
Wyatt Landers | Reviewed video tutorials for Blazor to better undertsand some pieces of the language that I was originally not understanding | Implementing changes to the front end as available for the pieces I have learned | Further clarification on tutorials may be needed as I learn more about the language

## Sprint 2 Scrum 2
Team Members | What was completed in the last 24 hours? | What will be completed in the next 24 hours? | Any impediments?
Jonathan Gamble | Added UI and UX enhancements to the application including advanced filters, loading bars to show progress and other minor fixes. | Consolidate all documentation to turn in for the Sprint 2 deliverable | No impediments at this time.
Terrence Shannon | Develop BDD test case, test User search functions, user profile | Review all Sprint 2 items and add log any bug fixes required for Sprint 2 tasks | No impediments at this time.
Shakera Dean | Edit the burndown chart to display the tasks that has been completed. Updated the scrum and the retro spreadsheet. | Continue to monitor the tasks and verify the change is being reflected on the burndown chart and assist the team where needed. | Could not assist the test site to see the changes that were made. Nothing will be done at this stage to resolve this issue because the rest of the team can assist the page. This issue did not have any affect on the sprint goals.
Miche Isaac | Reviewed Part 3 - Sprint 2 criteria Started testing App UI in multiple platform | Review Backlog Items for Part 4 Final Sprint | Potential Live testing and debugging
Wyatt Landers | Began work on changing front end pages to make the experience more eye catching for the user and to help myself understand formatting of the Blazor site implementations | Continue to work on the front end and the user experience as I keep learning about the frameworks. | No impediments at this time.