## Sprint 3 Scrum 1
Team Members | What was completed in the last 24 hours? | What will be completed in the next 24 hours? | Any impediments?
Jonathan Gamble | Completed the first three user stories for the sprint. | Begin working on the form chat group user story. | No impediments at this time.
Terrence Shannon | Perform tests on Sprint 3 items; | Document test results within test plan; Begin coding for Web UI changes / adjustments
Shakera Dean | Created a sprint and task that forces on the presentation,updated the scrum and retro document and created the burndown chart for sprint 3. Also added 3 tasks to sprint 3 to add more functions to the program. | Continue to make changes to the burndown chart to display the informaton correctly and test the functions added to the program for sprint 3. | No impediments
Miche Isaac | Tested Application UI in multiple browsers and desktop App | Continue Web UI as changes occurring Review and prepare documentation for next task | No impediments
Wyatt Landers | Altered some CSS and HTML for the website, giving it a new coat of paint. Created an icon for the website. | Continue to make changes to the CSS and HTML of the website. | No impediments.

## Sprint 3 Scrum 2
Team Members | What was completed in the last 24 hours? | What will be completed in the next 24 hours? | Any impediments?
Jonathan Gamble | Completed the form chat group user story. Completed the BDD Tests for Sprint 3. | Create 10 new unit tests and consolidate the material for the sprint 3 deliverable. Begin working on presentation. | No impediments at this time.
Terrence Shannon | Added functionality to edit account data from the main account page. Tested chat and messaging features. Begin documenting test results | Working on presentation and continue to document test results | None
Shakera Dean | Tested the new fucntions/features that were added to the site during sprint 3 and worked on my section of the presentation . Added a copy of the document that covers my section of the presentation to my task on the devops board for the team to review. | Make any changes to my presentation section based on the team feedback. | No impediments during this time
Miche Isaac | Presentation draft + UI testing | Final sprint testing. Presentation powerpoint | No impediments during this time
Wyatt Landers | Continued work on HTML and CSS elements. Created a user image for the profiles. Worked with Johnathan and Terrance on mob programming for a BDD Test. | Work on presentation and finish touching up if need be | No impediments.